**Timeline and Division of the Task:**

***Week 7-8:*** *Project Initiation and Literature Collection*

Determine the direction and goals of research.

Develop a feasible research pathway.

Collect references and prepare for the next step.

Develop a research plan and finalize the initial proposal.

***Week 9-10:*** *Data collection and Project Improvement*

Conduct an initial literature review to identify key references.

Design and publish questionnaires and collect and organize data.

Identify previous research and expected outputs.

Improve and refine the research outline.

***Week 11-12:*** *Outline Drawing up and Meaning Determination*

Combine with the research data analysis phenomenon and draw the conclusion.

Continue to enrich the literature search.

Draw up an outline and the conclusion of the project.

Clarify the value and practical significance of the research.

***Week 13-14:*** *Paper Writing and Project Preliminary Completion*

Discuss the division of work and define the direction of writing.

Make charts to enrich the structure of the paper.

Determine the writing context and write paper.

***Week 15-16:*** *Presentation Preparation and Project completion*

Preparation of presentation and conduct of group presentations.

Polish and revise the paper of the project.

Form a paper and report summary reflection.